## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1936/MURD/5 | 18/07/2023 | 18/07/2023 | Resource Division | 17.68 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under KAPASDANGA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000163/2023-2024 | 2088/MEDB | 19/06/2023 | 20/08/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 21.56 | 0 | 0 | 40
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | NEW SERVICE CONNECTION AT PH1 KAPASDANGA ID 304239449 |  |  | BILL/01410/2023-2024 | 307/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kapasdanga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000045/2023-2024 | 1103/MURD | 24/04/2023 | 24/05/2023 | MAMATA USHA ENTERPRISE | 21.38 | 11.06 | 51.73 | 65
5 | MURSHIDABAD | Burwan | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | Laying Distribution System Part-A, Rising Main, Construction of 200 Cum OHR, Boundwary Wall, Pump House, for Kapasdanga water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000020/2023-2024 | 993/MURD | 11/04/2023 | 01/01/2026 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 189.09 | 77.45 | 40.96 | 70
6 | MURSHIDABAD | Burwan | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | Laying Distribution System PART-B, FHTC for Kapasdanga water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. PART_B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000023/2023-2024 | 996/MURD | 11/04/2023 | 07/10/2025 | EVAN CONSTRUCTION PRIVATE LIMITED | 191.81 | 58.28 | 30.38 | 35
7 | MURSHIDABAD | Burwan | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | New | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 23/05/2025 | NADIA TUBEWELLS | 70.43 | 0 | 0 | 0
Total | [13 empty] | 515.13 | 146.79 | 28.5