## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER |  | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 01/12/2022 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000256/2023-2024 | 1219/MURD/41 | 03/05/2023 | 03/05/2023 | Resource Division | 31.36 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000389/2023-2024 | 526/MURD/06 | 19/02/2024 | 19/02/2024 | Resource Division | 14.88 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | Augmentation | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 02/10/2025 | M/S. MOHAN LAL JAIN | 2092.12 | 0 | 0 | 56
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natial Rajanagar Zone-II Piped water supply scheme Block_Raninagar II Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000547/2024-2025 | 351/MEDB | 10/02/2025 | 10/05/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 45.27 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000532/2024-2025 | 318/MEDB | 10/02/2025 | 10/05/2025 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 46.34 | 0 | 0 | 0
Total | [13 empty] | 2246.5 | 0 | 0