## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 04/04/2022 | MERCHANDISE-INDIA | 105.32 | 1.15 | 1.09 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 1180/MURD/07 | 29/04/2023 | 29/04/2023 | Resource Division | 134.73 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-A) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000127/2023-2024 | 1764/MURD | 06/07/2023 | 16/05/2026 | NADIA TUBEWELLS | 35.34 | 15.89 | 44.97 | 90
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Juranpur PH No-V |  |  | BILL/01445/2023-2024 | 341/WBSEDCL-JJM | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.44 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Juranpur PH No-IV |  |  | BILL/01444/2023-2024 | 340/WBSEDCL-JJM | 15/02/2024 | 15/02/2024 | WBSEDCL | 8.13 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Augmentation of JURANPUR (PART-A) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub Division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000082/2023-2024 | 1384/MURD | 22/05/2023 | 12/07/2026 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 456.53 | 361.23 | 79.12 | 20
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under JURANPUR ,PART-A ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001432/2023-2024 | 4312/MEDB | 29/12/2023 | 29/03/2024 | DAS CONSTRUCTION | 22.6 | 18.18 | 80.46 | 10
Total | [13 empty] | 767.08 | 396.45 | 51.68