## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Berhampore Mechanical | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Service connection charge for Bathur PH-I, Appl. no.3004523927. ID- 304212545. |  |  | BILL/01094/2023-2024 | 201/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 2.66 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Service connection charge for Bathur PH-II, Appl. no.3004523910. ID- 304212540. |  |  | BILL/01095/2023-2024 | 202/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 3.43 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Material Requisition To Resource Division |  |  | RTOR000333/2023-2024 | 79 | 09/01/2024 | 09/01/2024 | Resource Division | 3.37 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BATHUR ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000135/2023-2024 | 1923/MEDB | 16/06/2023 | 16/09/2023 | JOY BISHNU ENGINEERING CO. | 21.42 | 0 | 0 | 20
5 | MURSHIDABAD | Khargram | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Allied work for Construction of Pump House at Head Works Site &2nd T.W. Site,FHTC, Boundary Wall,Rising Main Connection, Laying Distribution System for Bathur PWSS in Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000038/2024-2025 | 1929/MURD | 03/07/2024 | 01/04/2025 | NOVELTY CONSTRUCTION | 43.95 | 0 | 0 | 10
6 | MURSHIDABAD | Khargram | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Formal work order for construction of Pump House at Head Work Site & 2nd Tube well site ,FHTC, Boundwary Wall, Rising Main Connection, Laying Distribution System for BATHUR PWSS in Khargram Block under Murshidabad Division ,PHE.Dte [ (i)Amount for LDS , R. Main, FHTC : Rs. 73,83,365.00 &(ii) Amount for Pump House, B.Wall : Rs. 35,86,277.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000793/2022-2023 | 593/MURD | 01/03/2023 | 05/11/2024 | NOVELTY CONSTRUCTION | 109.53 | 0 | 0 | 37
7 | MURSHIDABAD | Khargram | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | New | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bathur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000040/2023-2024 | 1100/MURD | 24/04/2023 | 24/05/2023 | NADIA TUBEWELLS | 21.35 | 0 | 0 | 100
Total | [13 empty] | 205.71 | 0 | 0