## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Berhampore Mechanical | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Badda ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000259/2023-2024 | 3695/MEDB | 03/11/2023 | 02/10/2025 | ORIENTAL ENGINEERING CO. | 22.53 | 0 | 0 | 70
2 | MURSHIDABAD | Burwan | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | BADDA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. (Part A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5 | ORD/000142/2023-2024 | 1866/MURD | 14/07/2023 | 01/01/2026 | DHIRENDRANATH MONDAL | 344.64 | 304.62 | 88.39 | 10
3 | MURSHIDABAD | Burwan | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | BADDA PWSS under Jal Jivan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5 | ORD/000095/2023-2024 | 1692/MURD | 28/06/2023 | 28/03/2026 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 226.02 | 21.15 | 9.36 | 10
4 | MURSHIDABAD | Burwan | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BADDA AND IT'S ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000392/2023-2024 | 2794/MURD | 04/09/2023 | 25/09/2023 | INDRAJIT MAZUMDAR | 18.45 | 15.55 | 84.3 | 100
5 | MURSHIDABAD | Burwan | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1075/MURD/18 | 19/04/2023 | 19/04/2023 | Resource Division | 24.74 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | NEW SERVICE CONNECTION AT PWSS BADDA PH1 ID 304248207 |  |  | BILL/01420/2023-2024 | 314/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 10.01 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Berhampore Mechanical | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | New | NEW SERVICE CONNECTION AT BADDA PH 2 C ID 304566360 |  |  | BILL/01477/2024-2025 | 431/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 7.6 | 0 | 0 | 0
Total | [13 empty] | 653.98 | 341.32 | 52.19