## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | New | Laying Distribution System Part-A , Rising Main Connection FHTC, for Kelai water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000051/2023-2024 | 1257/MURD | 08/05/2023 | 04/11/2023 | M/S CARE | 352.42 | 112.26 | 31.85 | 10
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | New | SHIFTING OF 11KV AT KELAI |  |  | BILL/01595/2023-2024 | 439/WBSEDCL-JJM | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | New | Formal work order for KELAI (PART-B) & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000843/2022-2023 | 753/MURD | 16/03/2023 | 01/01/2026 | NURTAJ SHAIKH | 217.79 | 96.35 | 44.24 | 18
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Kelai ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001484/2023-2024 | 763/MEDB | 20/02/2024 | 31/12/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 23.25 | 0 | 0 | 40
5 | MURSHIDABAD | Khargram | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kelai & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000038/2023-2024 | 1105/MURD | 24/04/2023 | 24/05/2023 | NADIA TUBEWELLS | 21.35 | 17.32 | 81.13 | 100
Total | [13 empty] | 618.19 | 225.93 | 36.55