## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Berhampore Mechanical | BADUA AND IT'S ADJOINING MOUJAS | SM/15682 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Badua ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000260/2023-2024 | 3696/MEDB | 03/11/2023 | 03/02/2024 | ORIENTAL ENGINEERING CO. | 23.45 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Murshidabad Division | BADUA AND IT'S ADJOINING MOUJAS | SM/15682 | New | Material Requisition To Resource Division |  |  | RTOR000244/2023-2024 | 1219/MURD/33 | 03/05/2023 | 03/05/2023 | Resource Division | 18.54 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Murshidabad Division | BADUA AND IT'S ADJOINING MOUJAS | SM/15682 | New | BADUA & adjoining mouzas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5 | ORD/000052/2023-2024 | 1263/MURD | 08/05/2023 | 30/11/2025 | TEKNO ENTERPRISE | 570.69 | 0 | 0 | 20
Total | [13 empty] | 612.68 | 0 | 0