## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1129/MURD/5 | 25/04/2023 | 25/04/2023 | Resource Division | 13.5 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | GAYESPUR PWSS under Jal Jeevan Mission of KHARGRAM Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000099/2023-2024 | 1700/MURD | 28/06/2023 | 12/12/2025 | SOFIQUL ISLAM | 279.31 | 0 | 0 | 10
3 | MURSHIDABAD | Khargram | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GAYESPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000628/2023-2024 | 3424/MURD | 02/11/2023 | 23/11/2023 | NADIA TUBEWELLS | 18.43 | 0 | 0 | 100
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | NEW SERVICE CONNECTION AT PH2 GAYESHPUR ID 304239446 |  |  | BILL/01414/2023-2024 | 305/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | NEW SERVICE CONNECTION AT PWSS PH1 GAYESHPUR ID 304239445 |  |  | BILL/01415/2023-2024 | 306/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 10.95 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | Construction of Drain, Laying of UPVC pipeline and road restoration work of Gayespur Water Supply Scheme in Khargram Block of Kandi Sub-Division, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000202/2024-2025 | 3285/MURD | 16/12/2024 | 15/01/2025 | DAS ENTERPRISE (SUBRATA DAS) | 38.28 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for GAYESPUR AND ADJOINING MOUJAS PWSS District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000566/2024-2025 | 348/MEDB | 10/02/2025 | 10/05/2025 | M/S SAJAHAN CHOWDHURY | 21.38 | 0 | 0 | 0
Total | [13 empty] | 385.62 | 0 | 0