## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1075/MURD/9 | 19/04/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | New | Berbari PH-2 Application No- 3004528419 |  |  | BILL/01201/2023-2024 | 277/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 3.24 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | New | Berbari PH-2 Application No- 3004528419 |  |  | BILL/01201/2023-2024 | 277/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 3.24 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | New | BERBARI PH-1 |  |  | BILL/01510/2023-2024 | 399/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 13.01 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | New | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000873/2022-2023 | 882/MURD | 28/03/2023 | 02/01/2024 | BANAMALI ENTERPRISES | 224.42 | 0 | 0 | 35
Total | [13 empty] | 245 | 0 | 0