## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER |  | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 24/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C |  | JUNIOR ENGINEER 1,JUNIOR HARIHARPARA BLOCK | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 1219/MURD/01 | 03/05/2023 | 03/05/2023 | Resource Division | 9.73 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Laying of Distribution System for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000134/2023-2024 | 1745/MURD | 06/07/2023 | 02/01/2024 | BENGAL ENTERPRISE | 84.67 | 0 | 0 | 70
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IB under SARBANGAPUR ground water based water supply scheme under Block_Nawda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001487/2023-2024 | 766/MEDB | 20/02/2024 | 20/05/2024 | M/S SAMRIDDHI ENTERPRISE | 23.48 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. (PART B- 55.0MTR.)_Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000024/2023-2024 | 1028/MURD | 13/04/2023 | 13/05/2023 | ABA CONTRACTOR | 4.63 | 0 | 0 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sarbangapur Zone -IB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000708/2023-2024 | 3806/MURD | 12/12/2023 | 02/01/2024 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 100
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 1811/MURD/17 | 20/06/2024 | 20/06/2024 | Resource Division | 9.93 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | NEW SERVICE CONNECTION AT SARBANGAPUR PWSS Z1 PART B PH 2 C ID 304506962 |  |  | BILL/01259/2024-2025 | 333/WBSEDCL-JJM | 19/12/2024 | 19/12/2024 | WBSEDCL | 3.44 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | NEW SERVICE CONNECTION AT SARBANGAPUR PWSS Z1 PART B PH 2 C ID 304506962 |  |  | BILL/01239/2024-2025 |  | 11/12/2024 | 11/12/2024 | WBSEDCL | 3.44 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Construction of 200 Cum OHR, Rising Main for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block, Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000226/2023-2024 | 2369/MURD | 04/08/2023 | 03/08/2025 | A.S. CONSTRUCTION | 114.35 | 0 | 0 | 100
12 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 22/12/2025 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 0 | 75
13 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Construction of Boundwary Wall , Pump House (Two nos), Construction of PCC approach road for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000846/2023-2024 | 779/MURD | 14/03/2024 | 28/11/2025 | STARK ENTERPRISE | 43.61 | 0 | 0 | 70
14 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Providing 1612 nos FHTC Connection for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division, PHE. Dte. |  | JUNIOR ENGINEER 3,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/000051/2024-2025 | 1976/MURD | 08/07/2024 | 22/08/2024 | DIPAK BHOWMIK | 84.07 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-I(Part -B) Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000030/2025-2026 | 1023/MURD | 05/05/2025 | 04/07/2025 | TANUSHREE ENTERPRISE | 23.01 | 0 | 0 | 0
Total | [13 empty] | 557.64 | 0 | 0