## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15743 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-IIA under Salar ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000241/2023-2024 | 3677/MEDB | 03/11/2023 | 03/02/2024 | SARKAR CONSTRUCTION | 21.35 | 0 | 0 | 10
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15743 | Augmentation | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 01/05/2025 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 0 | 20
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15743 | Augmentation | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 01/04/2025 | SUJIT KUMAR SAHA | 575.6 | 0 | 0 | 10
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15743 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,Junior Engineer 3,JUNIOR ENGINEER 5 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 01/01/2026 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
Total | [13 empty] | 1664.37 | 0 | 0