## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15745 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 0 | 76
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15745 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1004/MURD/2 | 11/04/2023 | 11/04/2023 | Resource Division | 49.59 | 0 | 0 | 0
3 | MURSHIDABAD |  | Central Drilling | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15745 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15745 | Augmentation | Laying of Rising Main , Distribution System, FHTC, OHR Repairing (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-I PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000439/2023-2024 | 2887/MURD | 12/09/2023 | 09/02/2024 | BURIMA CONSTRUCTION | 250.71 | 0 | 0 | 20
Total | [13 empty] | 21729.34 | 0 | 0