## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Tajsinghapur PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000832/2021-2022 | 3265/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 4.74 | 4.74 | 99.96 | 1
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Augmentation of TEJSINGHAPUR PWSS under Jal Jivan Mission of RANINAGAR - II Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000078/2023-2024 | 1383/MURD | 22/05/2023 | 01/01/2026 | PRADIP KUMAR DAS | 294.57 | 142.98 | 48.54 | 86
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Augmentation of TEJSINGHAPUR PWSS under Jal Jeevan Mission of RANINAGAR - II Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000164/2023-2024 | 1933/MURD | 18/07/2023 | 01/01/2026 | VOICE CONSTRUCTION | 293.06 | 12.95 | 4.42 | 35
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER_DOMKAL BLOCK | ORD/000104/2023-2024 | 1746/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 23.58 | 20.97 | 88.93 | 100
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 1167/MURD/39 | 28/04/2023 | 28/04/2023 | Resource Division | 79.35 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Balance work of Laying Distribution System , Road Restoration and other ancillary works of Tejsinghapur Water Supply Scheme within Raninagar-II Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000073/2025-2026 | 1259/MURD | 30/05/2025 | 29/07/2025 | DAS TRADING CO. | 64.29 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000564/2024-2025 | 346/MEDB | 10/02/2025 | 10/05/2025 | DAS ENTERPRISE (CHOA) | 23.19 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | Augmentation | NEW SERVICE CONNECTION AT TEJSINGHAPUR PH OHR AIRP C ID 304542843 |  |  | BILL/01342/2024-2025 | 377/WBSEDCL-JJM | 04/02/2025 | 04/02/2025 | WBSEDCL | 7.35 | 0 | 0 | 0
Total | [13 empty] | 790.12 | 181.64 | 22.99