## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15747 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 0 | 76
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15747 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
3 | MURSHIDABAD |  | Central Drilling | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15747 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15747 | Augmentation | Augmentation of BHARATPUR (ZONE -IIA) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000501/2023-2024 | 3088/MURD | 03/10/2023 | 21/10/2026 | SOFIQUL ISLAM | 423.46 | 0 | 0 | 50
Total | [13 empty] | 21949.99 | 0 | 0