## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 1043/MURD/3 | 17/04/2023 | 17/04/2023 | Resource Division | 31.92 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000310/2023-2024 | 1295/MURD/05 | 11/05/2023 | 11/05/2023 | Resource Division | 61.11 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III under Gokarna ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000225/2023-2024 | 3665/MEDB | 03/11/2023 | 03/02/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 34.39 | 25.63 | 74.52 | 60
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000342/2023-2024 | 79/MURD/09 | 09/01/2024 | 09/01/2024 | Resource Division | 31.88 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Construction of 600 Cum OHR, Pump House, Boundwary Wall , Rising Main Connection, Repairing of 2 nos P.H & Existing OHR for Augmentation of GOKARNA PWSS in Kandi Block , under Murshidabad Division ,PHE.Dte. (PART-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000030/2023-2024 | 1086/MURD | 20/04/2023 | 01/04/2025 | MD SAJAHAN ALI | 327.08 | 129.8 | 39.68 | 80
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000043/2023-2024 | 1141/MURD | 26/04/2023 | 01/04/2026 | M/S.TAPAS KUMAR CHAKRABORTY | 252.26 | 32.42 | 12.85 | 30
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte.(PART-C) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000042/2023-2024 | 1140/MURD | 26/04/2023 | 01/04/2026 | M/S.TAPAS KUMAR CHAKRABORTY | 358.04 | 154.01 | 43.02 | 30
8 | MURSHIDABAD |  | Central Drilling | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | Augmentation | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS GOKARNA PWSS Scheme, Block-KANDI to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/002151/2021-2022 | 3258/MURD | 05/10/2021 | 04/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.11 | 8.11 | 100 | 1
Total | [13 empty] | 22444.56 | 349.96 | 1.56