## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.37 | 4.89 | 76
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | Augmentation | Augmentation of Ground Water Based Burwan Zone-I PWSS of accommodate FHTC( 1848 Nos), Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Boundary Wall, 200 CUM OHR, Repairing of 272 CUM OHR in Burwan Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000351/2023-2024 | 2678/MURD | 24/08/2023 | 01/04/2025 | MOTI RAHAMAN | 360.93 | 64.27 | 17.81 | 10
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Burwan Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Burwan Block under Murshidabad Division, P.H. Engineering Dte |  |  | ORD/000727/2023-2024 | 3917/MURD | 21/12/2023 | 11/01/2024 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1004/MURD/3 | 11/04/2023 | 11/04/2023 | Resource Division | 70.9 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 1.73 | 1.77 | 80
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | Augmentation | Additional work for Augmentation of Burwan (Zone-I) PWSS of accommodate FHTC, Laying of Distribution System, Road Restoration work and Land Development in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000034/2025-2026 | 1111/MURD | 15/05/2025 | 14/07/2025 | MOTI RAHAMAN | 87.4 | 0 | 0 | 0
Total | [13 empty] | 717.78 | 70.37 | 9.8