## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. | SM/15837 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000394/2023-2024 | 526/MURD/04 | 19/02/2024 |  | Resource Division | 3.66 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. | SM/15837 | Augmentation | Formal work order for Augmentation of P T Rasulpur (Part - B) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000800/2022-2023 | 608/MURD | 02/03/2023 | 01/03/2024 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 363.24 | 75.85 | 20.88 | 20
Total | [13 empty] | 366.9 | 75.85 | 20.67