## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sultanpur (Village code 314726) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. | ASSISTANT ENGINEER | Junior Engineer | ORD/000242/2020-2021 | 85/MURD | 08/01/2021 | 09/03/2021 | DECON INDIA | 33.63 | 5.8 | 17.25 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 04/04/2022 | MERCHANDISE-INDIA | 105.32 | 10.28 | 9.76 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | Augmentation | Formal work order for Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part- A under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3 | ORD/000808/2022-2023 | 622/MURD | 03/03/2023 | 30/08/2023 | M/S. S. DAS AND ENTERPRISE | 508 | 351.34 | 69.16 | 20
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - I ) Part - A Water Supply Scheme at Head Work Site, 2nd Site site at Domkal Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 5 | ORD/000120/2023-2024 | 1761/MURD | 06/07/2023 | 27/07/2023 | R.K. DRILLING SERVICES | 23.58 | 20.58 | 87.28 | 50
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 1210/MURD/11 | 02/05/2023 | 02/05/2023 | Resource Division | 147.5 | 0 | 0 | 0
Total | [13 empty] | 818.03 | 388 | 47.43