## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1167/MURD/9 | 28/04/2023 | 28/04/2023 | Resource Division | 5.26 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Providing FHTC to 1200 nos household and OHR Repair of 45 cum capacity for Augmentation of Giria Zone -I and Zone-II Piped water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte . | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000097/2024-2025 | 2090/MURD | 23/07/2024 | 21/09/2024 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 60.76 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | EW SERVICE CONNECTION AT GIRIA Z1 PH3 ID 304512470 |  |  | BILL/01223/2024-2025 | 304/WBSEDL-JJM | 06/12/2024 | 06/12/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 01/12/2022 | STEELCONC AND ASSOCIATES | 12.39 | 2.52 | 20.33 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Augmentation of Ground Water Based Giria Zone-I PWS accommodate FHTC of 2614 nos household, Laying Distribution System, Laying Rising Main,Construction of Pump House (4.10m x 3.5m with sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of length 48 m, Repairing & maintenance of 2(two) nos Pump House ,existing boundary wall and Overhauling of R.C.C. elevated reservoir of 450 Cum capacity of staging hight 20 mtr. in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000585/2023-2024 | 3320/MURD | 22/10/2023 | 12/06/2026 | S.B. ASSOCIATES | 245.83 | 30.01 | 12.21 | 75
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Source Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. P.H.E. Dte. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000558/2024-2025 | 340/MEDB | 10/02/2025 | 10/05/2025 | M/S SAMRIDDHI ENTERPRISE | 36.36 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone-II & Giria Zone - I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000122/2023-2024 | 1767/MURD | 06/07/2023 | 31/12/2024 | R.K. DRILLING SERVICES | 23.58 | 7.74 | 32.81 | 100
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | NEW SERVICE CONNECTION AT GIRIA Z2 PH2 ID304531271 |  |  | BILL/01278/2024-2025 | 383/WBSEDCL-JJM | 10/02/2025 | 10/02/2025 | WBSEDCL | 0.92 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | NEW SERVICE CONNECTION AT GIRIA Z1 PH3 ID 304512470 |  |  | BILL/01216/2024-2025 |  | 02/12/2024 | 02/12/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | NEW SERVICE CONNECTION AT GIRIA Z2 PH1 ID 304531274 |  |  | BILL/01279/2024-2025 | 384/WBSEDCL-JJM | 10/02/2025 | 10/02/2025 | WBSEDCL | 5.25 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | Augmentation | Laying of Distribution System ,Rising Main and Extension of Boundary Wall for Augmentation of Giria Zone -I and Zone-II Piped water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000083/2024-2025 | 2076/MURD | 19/07/2024 | 17/09/2024 | M/S J.S. ENTERPRISE | 65.18 | 0 | 0 | 0
Total | [13 empty] | 462.59 | 40.26 | 8.7