## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under KADOA ,Part-A ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000129/2023-2024 | 1916/MEDB | 16/06/2023 | 16/09/2023 | S. G. TECHNICAL SERTIVCE | 35.09 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 1210/MURD/16 | 02/05/2023 | 02/05/2023 | Resource Division | 7.37 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | Augmentation | Laying of Rising Main, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Work, Construction of Boundary Wall (For T/W-I) =100 mtrs & Repair of Boundary Wall (50m +50m) =100 m at T/W-II site for Augmentation of KADOA (Zone - I) Part-A Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. (i)Amount for Construction Part: 5,87,696.00/ (ii)Amount for Pipeline Part: 22,96,300.00/- (Attached as Annexure -XII) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000781/2022-2023 | 685/MURD | 10/03/2023 | 06/09/2023 | M/S BAPPA ENTERPRISE | 28.81 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | Augmentation | Allied work of construction of culvert at kadoa Zone-I 2nd T.W site and approach road for H/W site & 2nd T.W site for Augmentation work under Jangipur sub division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000067/2024-2025 | 1988/MURD | 08/07/2024 | 06/09/2024 | M/S BAPPA ENTERPRISE | 16.72 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 2.61 | 3.53 | 100
Total | [13 empty] | 161.95 | 2.61 | 1.61