## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1147/MURD/2 | 27/04/2023 |  | Resource Division | 26.13 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of KADOA ground water based water supply scheme under Block- Suti-II Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000134/2023-2024 | 1921/MEDB | 16/06/2023 | 14/09/2023 | A.K. SIKDAR | 11.17 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.16 | 4.27 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER 6 | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 11/10/2024 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Quotation for Kadoa PH No-II |  |  | BILL/01435/2023-2024 | 328/WBSEDCL-JJM | 06/02/2024 |  | WBSEDCL | 11.21 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Quotation for Kadoa PH No-II |  |  | BILL/01435/2023-2024 | 328/WBSEDCL-JJM | 06/02/2024 |  | WBSEDCL | 11.21 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | NEW SERVICE CONNECTION AT KADOA Z2 PH1 ID304242107, Application NO 3004557257 |  |  | BILL/01409/2023-2024 | 330/WBSEDCL-JJM | 07/02/2024 |  | WBSEDCL | 4.38 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | NEW SERVICE CONNECTION AT KADOA Z2 PH1 ID304242107, Application NO 3004557257 |  |  | BILL/01409/2023-2024 | 330/WBSEDCL-JJM | 07/02/2024 |  | WBSEDCL | 4.38 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KADOA Zone -II Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000015/2024-2025 | 1754/MURD | 13/06/2024 | 04/07/2024 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 0
Total | [13 empty] | 2718.64 | 3.16 | 0.12