## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER |  | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 24/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C |  | JUNIOR ENGINEER 1,JUNIOR HARIHARPARA BLOCK | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 5.77 | 10.84 | 1
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000214/2023-2024 | 1219/MURD/05 | 03/05/2023 | 03/05/2023 | Resource Division | 46.14 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Construction Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr Boundary wall at 3rd Tubewell site of Sarbangapur Zone -II Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000039/2024-2025 | 1927/MURD | 03/07/2024 | 01/09/2024 | M/S S.R.K. ENTERPRISE | 16.6 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 1811/MURD/13 | 20/06/2024 | 20/06/2024 | Resource Division | 4.08 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Providing FHTC Connection to 193 nos household for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000136/2023-2024 | 1819/MURD | 12/07/2023 | 10/09/2023 | A.M. CONSTRUCTION | 21.14 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Laying of Distribution System, Rising Main for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000292/2023-2024 | 2646/MURD | 23/08/2023 | 01/08/2025 | DOBAY CONSTRUCTION | 229.82 | 145.35 | 63.25 | 70
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-II Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000052/2025-2026 | 1227/MURD | 28/05/2025 | 23/01/2026 | M/S.S.S. ENTERPRISE | 19.62 | 0 | 0 | 0
Total | [13 empty] | 420.08 | 151.13 | 35.98