## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1075/MURD/2 | 19/04/2023 | 19/04/2023 | Resource Division | 31.87 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | New | NEW SERVICE CONNECTION AT PWSS PH1 MANDALSAR ID 304239451 |  |  | BILL/01417/2023-2024 | 303/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 3.41 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | New | POWER CONNECTION AT PWSS PH2 MANDALSARPOWER CONNECTION AT PWSS PH2 MANDALSAR ID 304250313 |  |  | BILL/00179/2024-2025 | 44/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 7.8 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Murshidabad Division | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | New | Formal work order for MANDALSAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Khargram Block of Murshidabad District under Kandi Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000803/2022-2023 | 625/MURD | 03/03/2023 | 30/10/2025 | MOTI RAHAMAN | 359.46 | 0 | 0 | 30
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MANDALSAR ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000136/2023-2024 | 4309/MEDB | 29/12/2023 | 29/12/2025 | JOGMAYA ENGINEERING | 21.5 | 0 | 0 | 80
Total | [13 empty] | 424.04 | 0 | 0