## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | Laying Distribution System, FHTC of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. in the District of Murshidabad Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000025/2023-2024 | 1032/MURD | 13/04/2023 | 01/09/2025 | DIPAYAN DEY | 188.8 | 167.11 | 88.51 | 10
2 | MURSHIDABAD | Burwan | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | Construction of 200 Cum OHR, Pump House Boundwary Wall, , Rising Main Connection, Laying Distribution System of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. Part-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000021/2023-2024 | 995/MURD | 11/04/2023 | 01/04/2026 | APORUPA CONSTRUCTION | 226.95 | 113.24 | 49.9 | 65
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SUKURIA ground water based water supply scheme under Block_ Barwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000118/2023-2024 | 1907/MEDB | 16/06/2023 | 16/09/2023 | B. T. PROJECTS PVT. LTD. | 22.42 | 0 | 0 | 50
4 | MURSHIDABAD | Burwan | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURIA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000288/2023-2024 | 2634/MURD | 23/08/2023 | 13/09/2023 | SARKAR WATER SUPPLY AGENCY | 18.43 | 15.44 | 83.78 | 100
5 | MURSHIDABAD | Burwan | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 1936/MURD/4 | 18/07/2023 | 18/07/2023 | Resource Division | 15.94 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000133/2024-2025 | 2635/MURD | 23/09/2024 | 01/07/2025 | SABSAMAY | 9.85 | 0 | 0 | 80
7 | MURSHIDABAD | Burwan | Berhampore Mechanical | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | NEW SERVICE CONNECTION AT SUKURIA PH II, ID304233502 |  |  | BILL/01205/2023-2024 | 273/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 6.06 | 0 | 0 | 0
8 | MURSHIDABAD | Burwan | Berhampore Mechanical | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | New | NEW SERVICE CONNECTION AT SUKURIA PH I, ID 304233761 |  |  | BILL/01204/2023-2024 | 272/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 6.22 | 0 | 0 | 0
Total | [13 empty] | 494.68 | 295.79 | 59.79