## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Material Requisition To Resource Division |  |  | RTOR000286/2023-2024 | 1230/MURD/29 | 04/05/2023 | 04/05/2023 | Resource Division | 22.56 | 0 | 0 | 0
2 | MURSHIDABAD | Samserganj | Berhampore Mechanical | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KOHETPUR ground water based water supply scheme under Block_ Samsedganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000690/2023-2024 | 4304/MEDB | 29/12/2023 | 29/03/2024 | BHABANI PRASAD MANNA | 32.99 | 0 | 0 | 0
3 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Material Requisition To Resource Division |  |  | RTOR000373/2023-2024 | 495/MURD/08 | 15/02/2024 | 15/02/2024 | Resource Division | 8.37 | 0 | 0 | 0
4 | MURSHIDABAD | Samserganj | Berhampore Mechanical | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | NEW CONNECTION AT KOHETPUR PH-II |  |  | BILL/00422/2024-2025 | 143/WBSEDCL-JJM | 08/07/2024 | 08/07/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
5 | MURSHIDABAD | Samserganj | Berhampore Mechanical | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | NEW CONNECTION AT KOHETPUR PH-I |  |  | BILL/00423/2024-2025 | 144/WBSEDCL-JJM | 08/07/2024 | 08/07/2024 | WBSEDCL | 4.92 | 0 | 0 | 0
6 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | COST OF RESTORATION OF ROAD CONNECTTED TO NH-34 DHULIAN PAKUR ROAD AT CH. 4.275 TO 4.600. |  |  | BILL/01019/2024-2025 | 369-MSD/2024-20 | 12/09/2024 | 12/09/2024 | MURSHIDABAD HIGHWAY DIVISION-1 | 13.3 | 0 | 0 | 0
7 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000668/2022-2023 | 3409/MURD | 22/12/2022 | 05/02/2023 | R.K. DRILLING SERVICES | 23.56 | 0 | 0 | 0
8 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Formal work order for the work of KOHETPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000812/2022-2023 | 670/MURD | 09/03/2023 | 09/04/2025 | PRAFULLYA CONSTRUCTION | 379.82 | 141.31 | 37.2 | 22
9 | MURSHIDABAD | Samserganj | Central Drilling | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 7.58 | 1.65 | 10
10 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 17/06/2025 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
11 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.16 | 2.04 | 100
12 | MURSHIDABAD | Samserganj | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KOHETPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000275/2023-2024 | 2605/MURD | 22/08/2023 | 01/09/2025 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 50
Total | [13 empty] | 1302.57 | 154.05 | 11.83