## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.63 | 2.22 | 100
2 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Formal work order for MADHUPUR PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jiban Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000822/2022-2023 | 686/MURD | 10/03/2023 | 09/03/2024 | M/S KHAN CHOWDHURY BROTHERS AND CO | 224.5 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | MADHUPUR PWSS Construction to accommodate FHTC, Laying Distribution System , Rising Main under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000874/2022-2023 | 883/MURD | 28/03/2023 | 01/10/2025 | SHYAMAL KUMAR SAHA | 231.54 | 0 | 0 | 40
4 | MURSHIDABAD | Suti-II | Central Drilling | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 1230/MURD/28 | 04/05/2023 | 04/05/2023 | Resource Division | 33.76 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | NIMTITA -AURANGABAD ROAD DAMAGED OVER A LENGTH OF 850 M. |  |  | BILL/01605/2024-2025 | 594-MSD/2024-25 | 13/12/2024 | 13/12/2024 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 21.12 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Road restoration esxtimate of Nimtita Ghat Railway Station Road extended to Suti PS at Ch0.00 Km to 1.45 Km restoratio work for trench cut by PHED under Murshidabad Highway Division No - I, P.W. (Road) Dte. in the districyt of Murshidabad. |  |  | BILL/00009/2025-2026 |  | 21/04/2025 | 21/04/2025 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 15.88 | 0 | 0 | 0
Total | [13 empty] | 22119.81 | 5.63 | 0.03