## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Formal work order for MADHUPUR PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jiban Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000822/2022-2023 | 686/MURD | 10/03/2023 | 09/03/2024 | M/S KHAN CHOWDHURY BROTHERS AND CO | 224.5 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 1230/MURD/28 | 04/05/2023 | 04/05/2023 | Resource Division | 33.76 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | MADHUPUR PWSS Construction to accommodate FHTC, Laying Distribution System , Rising Main under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000874/2022-2023 | 883/MURD | 28/03/2023 | 01/10/2025 | SHYAMAL KUMAR SAHA | 231.54 | 0 | 0 | 40
4 | MURSHIDABAD | Suti-II | Central Drilling | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD | Suti-II | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.63 | 2.22 | 100
Total | [13 empty] | 22082.81 | 5.63 | 0.03