## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Domkal | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | New | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 01/12/2022 | MERCHANDISE-INDIA | 14.45 | 2.41 | 16.67 | 90
2 | MURSHIDABAD | Domkal | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | New | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3 | ORD/000868/2023-2024 | 832/MURD | 15/03/2024 | 05/04/2024 | NADIA TUBEWELLS | 11.78 | 10.93 | 92.78 | 100
3 | MURSHIDABAD | Domkal | Berhampore Mechanical | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Gokul Chak ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000652/2023-2024 | 3684/MEDB | 03/11/2023 | 03/02/2024 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 22.14 | 0 | 0 | 15
4 | MURSHIDABAD | Domkal | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | New | Construction of Ground Water Based Gokul Chak PWSS of accommodate FHTC(834 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall in Domkal Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000726/2023-2024 | 3953/MURD | 26/12/2023 | 21/07/2025 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 108.82 | 0 | 0 | 60
5 | MURSHIDABAD | Domkal | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000136/2024-2025 | 2637/MURD | 23/09/2024 | 20/02/2025 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
Total | [13 empty] | 165.91 | 13.34 | 8.04