## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- E village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000233/2023-2024 | 2343/MURD | 03/08/2023 | 02/10/2023 | SUGATA CHOWDHURY | 30.55 | 25.82 | 84.53 | 10
2 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- C village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000231/2023-2024 | 2342/MURD | 03/08/2023 | 02/10/2023 | M/S SAJAHAN CHOWDHURY | 30.48 | 12.67 | 41.56 | 10
3 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- B village, Block:- Khargram, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000230/2023-2024 | 2341/MURD | 03/08/2023 | 01/06/2026 | J.S. CONSTRUCTION | 30.54 | 0 | 0 | 15
4 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- D village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000478/2023-2024 | 3035/MURD | 27/09/2023 | 26/01/2026 | S.N. ENTERPRISE | 29.6 | 10.16 | 34.31 | 10
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works in connection to Accommodate FHTC at Kharsa Pump House-I ground water based water supply scheme under Block_ Khargram Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000500/2024-2025 | 51/MEDB | 09/01/2025 | 09/04/2025 | M/S SAMRIDDHI ENTERPRISE | 11.28 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works in connection to Accommodate FHTC at Kharsa Pump House-II ground water based water supply scheme under Block_ Khargram Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000501/2024-2025 | 52/MEDB | 09/01/2025 | 09/04/2025 | M/S SAMRIDDHI ENTERPRISE | 11.28 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | NEW SERVICE CONNECTION AT KHARSA PH 1 ID 304434820 |  |  | BILL/01085/2024-2025 | 260/WBSEDCL-JJM | 13/11/2024 | 13/11/2024 | WBSEDCL | 3.47 | 0 | 0 | 0
8 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- A village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000254/2023-2024 | 2494/MURD | 11/08/2023 | 01/06/2026 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 30.55 | 0 | 0 | 20
9 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II under JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II and KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000017/2025-2026 | 1141/MEDB | 14/05/2025 | 05/06/2026 | M/S K.P. PRAMANIK | 11.64 | 0 | 0 | 20
Total | [13 empty] | 189.39 | 48.65 | 25.69