## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1075/MURD/11 | 19/04/2023 | 19/04/2023 | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under GUNDIRIA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000269/2023-2024 | 3706/MEDB | 03/11/2023 | 03/02/2024 | M/S SAJAHAN CHOWDHURY | 21.21 | 11.7 | 55.14 | 35
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | GUNDIRIA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5,JUNIOR ENGINEER 8 | ORD/000149/2023-2024 | 1898/MURD | 17/07/2023 | 01/04/2025 | MAA MANSAHA CONSTRUCTION | 119.11 | 0 | 0 | 65
Total | [13 empty] | 141.42 | 11.7 | 8.27