## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1075/MURD/11 | 19/04/2023 | 19/04/2023 | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under GUNDIRIA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000269/2023-2024 | 3706/MEDB | 03/11/2023 | 03/02/2024 | M/S SAJAHAN CHOWDHURY | 21.21 | 0 | 0 | 35
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | GUNDIRIA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5,JUNIOR ENGINEER 8 | ORD/000149/2023-2024 | 1898/MURD | 17/07/2023 | 01/04/2025 | MAA MANSAHA CONSTRUCTION | 119.11 | 0 | 0 | 65
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UJUNIA SISUA AND GUNDIRIA Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur I & II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 8 | ORD/000624/2023-2024 | 3409/MURD | 02/11/2023 | 16/02/2025 | GENUINE | 18.43 | 0 | 0 | 100
Total | [13 empty] | 159.85 | 0 | 0