## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | New | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 1219/MURD/10 | 03/05/2023 | 03/05/2023 | Resource Division | 0.76 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Matua ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000254/2023-2024 | 4317/MEDB | 29/12/2023 | 29/03/2024 | H.K. DAS & CO. | 8.93 | 5.69 | 63.76 | 10
3 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | New | Construction of Pump House, Boundary Wall , Path Way of Matua PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000830/2023-2024 | 780/MURD | 14/03/2024 | 28/04/2024 | SANTA TRADING | 14.19 | 3.75 | 26.45 | 90
4 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | New | Matwa PH-1 Application no- 3004547182 |  |  | BILL/01181/2023-2024 | 237/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 7.87 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | New | NEW CONNECTION AT MATWA PH-II |  |  | BILL/00229/2024-2025 | 69/WBSEDCL-JJM | 09/05/2024 | 09/05/2024 | WBSEDCL | 2.96 | 0 | 0 | 0
Total | [13 empty] | 34.71 | 9.44 | 27.21