## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1129/MURD/1 | 25/04/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Pulia ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000256/2023-2024 | 3692/MEDB | 03/11/2023 | 01/02/2024 | ASHUTOSH DAS & CO. | 21.24 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | Pulia PH-1 Application No-3004547904 |  |  | BILL/01172/2023-2024 | 235/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 5.22 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | Pulia PH-1 Application No-3004547904 |  |  | BILL/01172/2023-2024 | 235/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 5.22 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | Pulia PH-2 App No- 3004547976 |  |  | BILL/01173/2023-2024 | 236/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 5.46 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Central Drilling | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 29/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Murshidabad Division | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | New | PULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000097/2023-2024 | 1698/MURD | 28/06/2023 | 26/10/2023 | ESCON INDIA | 134.38 | 21.44 | 15.96 | 10
Total | [13 empty] | 283.67 | 21.44 | 7.56