## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 06/09/2021 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IA under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000232/2023-2024 | 3669/MEDB | 03/11/2023 | 03/02/2024 | M/S SAJAHAN CHOWDHURY | 22.78 | 0 | 0 | 70
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 12/11/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | POWER CONNECTION AT PWSS PH1 Z 1A MADEBNAGAR APPLICATION NO.3004627412 |  |  | BILL/00188/2024-2025 | 42/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 7.09 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 243/5 & 243/6) on railway land of mouza-Jigari kulgachi & Connecting with existing 150 mm dia Rising main line of Mahadevnagar Zone - I ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000424/2021-2022 | 2478/MURD | 16/08/2021 | 15/10/2021 | DECON INDIA | 26.25 | 0 | 0 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000123/2023-2024 | 1773/MURD | 06/07/2023 | 31/05/2025 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 80
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 13/10/2024 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 0 | 0 | 100
Total | [13 empty] | 219.16 | 0 | 0