## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16171 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1167/MURD/26 | 28/04/2023 | 28/04/2023 | Resource Division | 61.81 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16171 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHASIPAIKAR ZONE-IIB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000555/2023-2024 | 3194/MURD | 12/10/2023 | 02/11/2023 | TAPAN DAS | 23.72 | 0 | 0 | 50
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16171 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 30/10/2024 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
Total | [13 empty] | 2098.25 | 0 | 0