## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 09/06/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IC under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000234/2023-2024 | 3671/MEDB | 03/11/2023 | 03/02/2024 | M/S SAMRIDDHI ENTERPRISE | 22.92 | 0 | 0 | 50
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 12/11/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | Augmentation | Renovation of Modified Sujapur Sadhipur Model of AIRP (Capacity 123 Cum/hr.) at Mahadebnagar Zone I Water Supply Scheme of Farakka Block Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000248/2024-2025 | 226/MURD | 27/01/2025 | 13/03/2025 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 77.24 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000119/2023-2024 | 1771/MURD | 06/07/2023 | 20/05/2025 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 40
Total | [13 empty] | 191.3 | 0 | 0