## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 1167/MURD/38 | 28/04/2023 | 28/04/2023 | Resource Division | 5.48 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 9.6 | 2.79 | 29.11 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000107/2023-2024 | 1749/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 35.37 | 10.27 | 29.04 | 40
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer | ORD/000695/2023-2024 | 3768/MURD | 08/12/2023 | 29/12/2023 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000395/2023-2024 | 526/MURD/08 | 19/02/2024 | 19/02/2024 | Resource Division | 2.46 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | NEW CONNECTION KUPILA PH-1 |  |  | BILL/01610/2023-2024 | 438/WBSEDCL-JJM | 13/03/2024 | 13/03/2024 | WBSEDCL | 6 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 29/01/2026 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 0 | 20
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Augmentation of KUPILA PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000077/2023-2024 | 1380/MURD | 22/05/2023 | 31/03/2026 | S.S. ENTERPRISE | 413.75 | 238.83 | 57.72 | 30
9 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Kupila ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000655/2023-2024 | 3689/MEDB | 03/11/2023 | 02/04/2027 | EASTERN INDIA SALES & SERVICE | 22.33 | 15.74 | 70.5 | 10
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000136/2024-2025 | 2637/MURD | 23/09/2024 | 20/02/2025 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
Total | [13 empty] | 548.12 | 267.63 | 48.83