## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 18/08/2022 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000705/2023-2024 | 3813/MURD | 12/12/2023 | 02/01/2024 | HARUN ALL RASHID & BROTHERS | 11.77 | 0 | 0 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 1210/MURD/08 | 02/05/2023 | 02/05/2023 | Resource Division | 9.5 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | Augmentation | Providing FHTC Connection to 268 nos household, Laying of Rising Main, Laying of Distribution System, overhauling of RCC 45 Cum OHR, Construction of Boundary Wall (For T/W-I) =100mtr, Special repair and renovation of existing 1 (One) Nos Pump House and Allied Works and Construction of RCC approach road =140 mtr for Augmentation of Jadabpur Nimtala Piped Water Supply Scheme in Farakka Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000819/2023-2024 | 740/MURD | 12/03/2024 | 11/05/2024 | PAL CONSTRUCTION | 57.61 | 26.63 | 46.23 | 50
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000553/2024-2025 | 335/MEDB | 10/02/2025 | 10/05/2025 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 21.52 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | Augmentation | Sinking of 04 (Four) Nos 200 mm dia tube well by DTH method using UPVC Pipe at Adwaita Nagar CT T.W-I,II & Jadabpur Nimtala T.W-I,II Water Supply Scheme of Samserganj , Farakka under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000495/2024-2025 | 665/MURD | 19/03/2025 | 26/08/2025 | KHOKAN BISWAS | 24.89 | 0 | 0 | 100
Total | [13 empty] | 135.07 | 26.63 | 19.72