## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 1180/MURD/26 | 29/04/2023 |  | Resource Division | 52.49 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | Augmentation | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000898/2022-2023 | 1082/ MURD | 27/04/2022 | 11/06/2022 | MARUTI CONSTRUCTION AND CO. | 62.56 | 7.17 | 11.47 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDHUA ZONE -I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION,JUNIOR ENGINEER 3 | ORD/000710/2023-2024 | 3814/MURD | 12/12/2023 | 02/01/2024 | HARUN ALL RASHID & BROTHERS | 23.52 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | Augmentation | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 15/01/2025 | NAYLA CONSTRUCTION | 836.98 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 18/08/2022 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
Total | [13 empty] | 985.35 | 7.17 | 0.73