## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/16178 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/16178 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 1219/MURD/34 | 03/05/2023 | 03/05/2023 | Resource Division | 2.92 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/16178 | Augmentation | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 01/04/2025 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 0 | 10
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/16178 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 13/10/2024 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
Total | [13 empty] | 1287.69 | 0 | 0