## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Berhampore Mechanical | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16214 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sujapur Part-B village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000212/2023-2024 | 3072/MEDB | 02/08/2023 | 02/11/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16214 | New | Ground Water based water supply scheme for Sujapur Part- B village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer, Estimating Section | ORD/000209/2023-2024 | 2320/MURD | 02/08/2023 | 01/11/2025 | SOUVIK HALDER | 30.54 | 0 | 0 | 60
3 | MURSHIDABAD | Khargram | Murshidabad Division | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16214 | New | Ground Water based piped water supply scheme for Sujapur Part- A village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer, Estimating Section | ORD/000495/2023-2024 | 3054/MURD | 29/09/2023 | 31/12/2025 | M/S BHATTACHARJEE & CO | 30.55 | 2.85 | 9.34 | 42
Total | [13 empty] | 67.4 | 2.85 | 4.23