## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-A village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000192/2023-2024 | 3051/MEDB | 02/08/2023 | 31/10/2023 | SARKAR CONSTRUCTION | 6.3 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-C village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000194/2023-2024 | 3053/MEDB | 02/08/2023 | 31/10/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-D village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000195/2023-2024 | 3054/MEDB | 02/08/2023 | 31/10/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-B village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000193/2023-2024 | 3052/MEDB | 02/08/2023 | 31/10/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- C village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000213/2023-2024 | 2323/MURD | 02/08/2023 | 01/10/2023 | M/S. MONDAL ENTERPRISE | 30.25 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- D village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000216/2023-2024 | 2327/MURD | 02/08/2023 | 01/10/2023 | U.S BUILDERS | 30.54 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- A village, Block:- Burwan, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000194/2023-2024 | 2024/MURD | 25/07/2023 | 23/09/2023 | M/S S.R.K. ENTERPRISE | 30.55 | 0 | 0 | 0
8 | MURSHIDABAD | Burwan | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- B village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000212/2023-2024 | 2322/MURD | 02/08/2023 | 01/10/2023 | KESHAB CHANDRA DAS | 30.54 | 0 | 0 | 0
Total | [13 empty] | 147.09 | 0 | 0