## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 3.11 | 1.23 | 100
2 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | BAJITPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer 3 | ORD/000011/2023-2024 | 959/MURD | 05/04/2023 | 01/10/2026 | CHABDAR ALI TRADERS | 233.79 | 74.67 | 31.94 | 85
3 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | Material Requisition To Resource Division |  |  | RTOR000275/2023-2024 | 1230/MURD/18 | 04/05/2023 | 04/05/2023 | Resource Division | 29.58 | 0 | 0 | 0
4 | MURSHIDABAD | Raghunathganj-II | Central Drilling | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 0 | 10
5 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bajitpur Water Supply Scheme at Raghunathganj-II Block of Jangipur Sub Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 2 | ORD/000100/2024-2025 | 2132/MURD | 26/07/2024 | 01/03/2025 | TARIKUL SK | 20.52 | 0 | 0 | 100
6 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | Material Requisition To Resource Division |  |  | RTOR000377/2023-2024 | 495/MURD/04 | 15/02/2024 | 15/02/2024 | Resource Division | 5.54 | 0 | 0 | 0
7 | MURSHIDABAD | Raghunathganj-II | Berhampore Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for BAJITPUR PIPED WATER SUPPLY SCHEME. District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000555/2024-2025 | 337/MEDB | 10/02/2025 | 01/08/2026 | M/S SAJAHAN CHOWDHURY | 21.38 | 0 | 0 | 60
8 | MURSHIDABAD | Raghunathganj-II | Berhampore Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | NEW SERVICE CONNECTION AT BAJITPUR PH 1 ID 304531273 |  |  | BILL/01276/2024-2025 | 367/WBSEDCL-JJM | 21/01/2025 | 21/01/2025 | WBSEDCL | 4.96 | 0 | 0 | 0
9 | MURSHIDABAD | Raghunathganj-II | Berhampore Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | New | NEW SERVICE CONNECTION AT BAJITPUR PH 2 ID 304531272 |  |  | BILL/01277/2024-2025 | 368/WBSEDCL-JJM | 21/01/2025 | 21/01/2025 | WBSEDCL | 5 | 0 | 0 | 0
Total | [13 empty] | 1032.7 | 77.77 | 7.53