## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-I | Berhampore Mechanical | CHANDAMARI PIPED WATER SUPPLY SCHEME. | SM/16218 | New | NEW CONNECTION AT CHANDAMARI PH-I |  |  | BILL/00428/2024-2025 | 140/WBSEDCL-JJM | 08/07/2024 | 08/07/2024 | WBSEDCL | 7.27 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-I | Berhampore Mechanical | CHANDAMARI PIPED WATER SUPPLY SCHEME. | SM/16218 | New | NEW CONNECTION AT CHANDAMARI PH-II |  |  | BILL/01240/2024-2025 |  | 11/12/2024 | 11/12/2024 | WBSEDCL | 4.31 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-I | Murshidabad Division | CHANDAMARI PIPED WATER SUPPLY SCHEME. | SM/16218 | New | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 01/01/2026 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 0 | 10
4 | MURSHIDABAD | Suti-I | Murshidabad Division | CHANDAMARI PIPED WATER SUPPLY SCHEME. | SM/16218 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 3.26 | 1.29 | 100
Total | [13 empty] | 2523 | 3.26 | 0.13