## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | Formal work order for the Work of Augmentation of KHAYRAMARI PART-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3,JUNIOR ENGINEER 8 | ORD/000809/2022-2023 | 657/MURD | 06/03/2023 | 26/06/2025 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 466.36 | 285.91 | 61.31 | 95
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,Part-A under Khayramari ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000653/2023-2024 | 3687/MEDB | 03/11/2023 | 03/02/2024 | SUBHRA ENTERPRISE | 11.18 | 7.16 | 64.06 | 70
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5,JUNIOR ENGINEER_JALANGI BLOCK | ORD/000103/2023-2024 | 1744/MURD | 06/07/2023 | 20/07/2023 | SARKAR WATER SUPPLY AGENCY | 9.22 | 0 | 0 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 1180/MURD/18 | 29/04/2023 | 29/04/2023 | Resource Division | 179.05 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | New connection charge for Khairamari W/S Scheme (Part-A), P/H No.-II. |  |  | BILL/00276/2023-2024 | 95/WBSEDCL-JJM | 11/08/2023 | 11/08/2023 | WBSEDCL | 0.7 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2024 to 30.05.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000788/2023-2024 | 17/KSD | 16/01/2024 | 15/05/2024 | SOUMYADIP MISRA | 0.69 | 1.53 | 220.6 | 70
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | MURD/2481/04 | 04/09/2024 | 04/09/2024 | Resource Division | 5.07 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | Augmentation | ADDL SERVICE CONNECTION CHARGES KHAIRAMARI PWSS PART A PH 2,ID860281602 |  |  | BILL/01110/2023-2024 | 207/WBSEDCL-JJM | 02/01/2024 | 02/01/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
Total | [13 empty] | 675.5 | 294.6 | 43.61