## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-II under Loknathpur ground water based water supply scheme under Block_ Beldanga-II, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000252/2023-2024 | 3690/MEDB | 03/11/2023 | 03/02/2024 | GOENKA ENTERPRISE | 33.83 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 1180/MURD/29 | 29/04/2023 | 29/04/2023 | Resource Division | 45.89 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 23/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 12.36 | 26.12 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 2.84 | 2.91 | 80
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 1811/MURD/23 | 20/06/2024 | 20/06/2024 | Resource Division | 7.29 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | NEW CONNECTION AT LOKNATHPUR Z-II PH-I |  |  | BILL/01577/2023-2024 | 417/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 4.52 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Lalgola, Beldanga II and Bharatpur I and II block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000054/2025-2026 | 45/5 | 29/05/2025 | 29/08/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 16.41 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Laying Distribution System For Augmentation of Loknathpur Zone-II (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000868/2022-2023 | 847/MURD | 24/03/2023 | 01/07/2025 | SOMA CONSTRUCTION | 154.95 | 0 | 0 | 40
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Augmentation of Ground Water Based Loknathpur zone-II PWSS to accommodate FHTC of 600 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 170 m and Soil Investigation & 200 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000538/2023-2024 | 3147/MURD | 09/10/2023 | 16/05/2024 | M H SUPPLIERS | 210.2 | 0 | 0 | 8
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for LOKNATHPUR ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000037/2025-2026 | 1130/MURD | 16/05/2025 | 15/07/2025 | MARUTI CONSTRUCTION AND CO. | 23.01 | 0 | 0 | 0
Total | [13 empty] | 640.9 | 15.2 | 2.37