## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/16248 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SANTOSHPUR ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000104/2023-2024 | 1892/MEDB | 16/06/2023 | 14/09/2023 | S. P. CONSTRUCTION | 22.53 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/16248 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Santoshpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000169/2023-2024 | 2092/MEDB | 19/06/2023 | 17/09/2023 | M/S SAMRIDDHI ENTERPRISE | 21.11 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/16248 | New | SANTOSHPUR PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER |  | ORD/000546/2023-2024 | 3179/MURD | 11/10/2023 | 06/08/2024 | GARAI INFRA PROJECT | 260.08 | 0 | 0 | 0
Total | [13 empty] | 303.72 | 0 | 0