## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16265 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-III under MURADPUR JALANGI ground water based water supply scheme under Block_ JALANGI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000111/2023-2024 | 3719/MEDB | 03/11/2023 | 03/02/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 21.43 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16265 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 04/04/2022 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 0 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16265 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000237/2023-2024 | 1219/MURD/25 | 03/05/2023 | 03/05/2023 | Resource Division | 10.21 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16265 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 21/08/2025 | ULTRA CONSTRUCTION. | 100.45 | 0 | 0 | 95
Total | [13 empty] | 160.71 | 0 | 0