## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BINDARPUR ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000052/2023-2024 | 1925/MEDB | 16/06/2023 | 16/09/2023 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 35.06 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1075/MURD | 19/04/2023 | 19/04/2023 | Resource Division | 31.02 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | BINDARPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-I of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000286/2023-2024 | 2641/MURD | 23/08/2023 | 01/09/2025 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 606.88 | 0 | 0 | 20
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | Surfacing with 20 mm th P.C. and S.C. and restoration for damage by PHE pipeline with GSB, WBM II and allied works of Kalitala Jajan extension upto Ruhaghat Road from 0.00 km to 10.00 km under Berhmapore Division No - I, PWD during the year 2024-25 |  |  | BILL/01808/2024-2025 | 610-MSD/2024-25 | 22/01/2025 | 22/01/2025 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 81.83 | 0 | 0 | 0
Total | [13 empty] | 754.79 | 0 | 0