## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BINDARPUR ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000052/2023-2024 | 1925/MEDB | 16/06/2023 | 16/09/2023 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 35.06 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1075/MURD | 19/04/2023 | 19/04/2023 | Resource Division | 31.02 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | New | BINDARPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-I of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000286/2023-2024 | 2641/MURD | 23/08/2023 | 01/09/2025 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 606.88 | 0 | 0 | 20
Total | [13 empty] | 672.96 | 0 | 0